[COMPANY NAME]  –  COMPANY PROCEDURE

RAMS PREPARATION PACK

How the office prepares, checks, issues and controls a RAMS pack (risk assessments and method statement) for a job, so that the client gets a site-specific pack and the crew gets the same plan on the day.

| Reference | Version | Date issued | Review date |
| --- | --- | --- | --- |
| ARB-ACP-07 | 2.0 | [DD/MM/YYYY] | [DD/MM/YYYY] |

| At a glance |  |
| --- | --- |
| What it is for | A correct, site-specific, approved RAMS pack for every job that needs one, issued on time and version-controlled. |
| Who does it | Office Administrator or Compliance Lead assembles it. The Surveyor or Operations Manager gives the technical input. A Manager or Director approves it. |
| When (the trigger) | The client or principal contractor asks for RAMS; the contract requires it; the work is higher risk; or we are working on a commercial, construction or utility site. |
| Time needed | About 1–2 hours for a typical job once the survey is done. Longer for construction sites, highways or complex rigging. |
| You will need | The accepted quote and survey (ARB-SITE-001), the Job Sheet (ARB-SITE-002), the Method Statement form (ARB-SITE-005), our GRA and COSHH library, and the client’s requirements. |
| What "done" looks like | Approved pack issued, client acceptance saved, the final version handed to the Team Leader, and the signed SSRA and briefing record back in the job file. |
| Where records go | Job file → RAMS folder, with a sub-folder per revision. Kept for [6 years] after the job. |

Where this fits in the office flow

| Enquiry | › | TPO / CA check ACP-01 | › | Quote ACP-08 | › | RAMS ACP-07 THIS PROCEDURE | › | Job | › | Invoice ACP-08 | › | Credit control ACP-06 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

RAMS are prepared after the quote is accepted and permissions are in place, and before the job is scheduled (ARB-ACP-08, stage 7).

The rule No work starts where RAMS are required until the pack is approved internally and issued, and any client comments are dealt with. The office writes the Method Statement before the job. The Site Specific Risk Assessment (ARB-SITE-004) is always completed by the Team Leader on site, on the day (ARB-POL-01 section 5.1). A RAMS pack never replaces it.

1     What goes in a RAMS pack

Section 1 of 5  ·  About 2 minutes to read  ·  Office, Manager

| Part of the pack | Our document | Who prepares it, and when |
| --- | --- | --- |
| Method statement | ARB-SITE-005 Method Statement (12 sections, from CDM and scope to rescue, acceptance and revisions) | Manager or estimator, before the job |
| Generic risk assessments | The GRAs that apply to this job only, from our GRA library [ref] (the list is in SSRA section 7) | Office selects; Manager checks |
| Site-specific hazards | Known hazards from the survey (ARB-SITE-001 section 5) written into the Method Statement. The SSRA (ARB-SITE-004) confirms them on the day. | Surveyor; Team Leader on the day |
| COSHH | COSHH assessments for the substances in Method Statement section 4 (e.g. fuels, chain oil, herbicide) | Office |
| Supporting evidence | Insurance, training matrix, plant and LOLER records, policies, accreditations, permissions, wildlife check, traffic plan | Office, as the client asks |

2     Step by step

Section 2 of 5  ·  About 1–2 hours per pack  ·  Office, Surveyor, Manager, Team Leader

| # | What to do | Who | Record it |
| --- | --- | --- | --- |
| 1 | Confirm RAMS are needed, and the deadline RAMS are needed when the client or principal contractor asks, the contract requires it, the work is higher risk (e.g. climbing, rigging over structures, MEWPs, work near roads or lines), or the site is commercial, construction or utility. Record the client’s deadline. Where the contract requires it, issue at least [48 hours / 2 working days] before work starts, or earlier if the client says so. | Office | Job Sheet section 3; diary deadline |

| 2 | Gather the project information Collect the full scope (from the accepted quote), site address, client requirements, programme dates, access arrangements and any known hazards. Use the survey: access (section 2), trees and work (3), permissions and wildlife (4), hazards (5) and photos. Ask the principal contractor for their site rules, induction and construction phase plan. | Office, with the Surveyor | Job file → RAMS folder |
| --- | --- | --- | --- |

| 3 | Select the relevant GRAs Choose only the Generic Risk Assessments that apply to this job, e.g. aerial tree work, rigging, chipping, stump grinding, traffic management. Check each one has been reviewed in the last 12 months. | Office; Manager checks | List of GRAs in Method Statement section 11 |
| --- | --- | --- | --- |

| 4 | Make the site-specific hazards specific Write the real hazards for this site into the Method Statement, not generic wording: access and egress, public interface, overhead and underground utilities, environmental constraints, and emergency arrangements. e.g. "BT line crosses the front of T3 at 6 m – sections lowered away from it", not "beware of services". If the client wants an SSRA in advance, send a pre-start copy of ARB-SITE-004 with sections 1 to 5 filled in from the survey and marked "Pre-start – completed and signed on the day". | Surveyor / Operations Manager | Method Statement sections 2, 7, 8, 9, 10 |
| --- | --- | --- | --- |

| 5 | Draft the Method Statement (ARB-SITE-005) Complete it for this site, including: - plant and equipment (section 4) and the numbered sequence of work (5) - rigging plan (6), traffic and pedestrian management (7) - waste handling (9), crew and supervision (3) - emergency and aerial rescue arrangements, with a named rescuer for any climbing (10) It must match the risk assessments and how the crew really works. Do not copy the last job’s method statement. | Manager or estimator | Method Statement, status "Draft" |
| --- | --- | --- | --- |

| 6 | Attach the supporting documents Add what the client asked for, and tick Method Statement section 11. Check every date. Nothing expired: insurance, training certificates, LOLER examinations, accreditations. Send the training matrix, not personal documents, unless the client needs certificate copies (ARB-POL-04). | Office | Pack index (Section 4) |
| --- | --- | --- | --- |

| 7 | Internal review and approval A Manager or Director checks: correct project details and job reference; the right GRAs; the method matches the scope; the rescue plan and emergency details are complete; no out-of-date documents; and no other client’s name, site or photos in the pack. Then signs "Approved by" in Method Statement section 12. | Manager / Director | Method Statement section 12 approval; status "Final" |
| --- | --- | --- | --- |

| 8 | Issue to the client, and control versions Send by email or the client portal as one PDF with a pack index. Record the date issued and keep the sent email or portal receipt. Where required, ask for written acceptance (Method Statement section 12) and deal with every comment before mobilising. Every pack carries a revision letter and issue date (e.g. Rev A, 01/10/2026). If anything changes, update the revision log in section 12, re-approve and re-issue. Keep old versions, marked "SUPERSEDED". | Office; Manager approves changes | RAMS log; sent email; acceptance; revision log; superseded copies |
| --- | --- | --- | --- |

| 9 | Hand over and brief on site Give the Team Leader the final pack with the Job Sheet. On the day, the Team Leader checks the method against the site, completes the SSRA, briefs everyone (including subcontractors and visitors) and gets the signatures: SSRA section 8 and Method Statement section 12. If the site is not as planned, stop: a Manager agrees the change, the revision is recorded and the crew is re-briefed. | Office; Team Leader | Signed SSRA and briefing log back in the job file |
| --- | --- | --- | --- |

3     When to stop, and an example

Section 3 of 5  ·  About 2 minutes to read  ·  Office, Manager, Team Leader

Stop – do not continue if… - RAMS are required and the pack is not approved, issued, or accepted where acceptance is needed; - a generic or old pack is being reused without a project-specific review; - any insurance, certificate, LOLER examination or accreditation in the pack has expired; - the client or principal contractor has made comments that are not yet resolved; - there is climbing or aerial work and no named aerial rescuer (no aerial rescuer, no climb); - overhead power lines are within 10 m, or 2 tree lengths for felling, and the network operator has not been consulted (ARB-POL-01 section 10.2); - a TPO consent, conservation area notice, felling licence or wildlife check is missing; - it is construction work and the construction phase plan or site induction is not in place (CDM 2015). If any of these apply, stop and speak to [Manager name]. Do not schedule the job (ARB-ACP-08).

What this means for you A principal contractor asks for RAMS to clear six sycamores on a housing site, due 3 working days before start. The survey shows an 11 kV line along the boundary and a public footpath. You select the felling, rigging, chipping and traffic GRAs, and the Manager writes the sequence: sections lowered away from the line, footpath closed with a marked diversion, and the network operator’s agreed method attached. You add insurance, the training matrix and the chipper’s service record. The Director spots the old pack’s logo and another client’s site photo in the appendix and removes them before approving Rev A. The PC comments on the welfare section; you update to Rev B, mark Rev A "SUPERSEDED" and re-issue. On the day, the Team Leader completes the SSRA and briefs the crew.

4     Templates

Section 4 of 5  ·  Copy, paste and fill in  ·  Office

Issue email Subject: RAMS – [site address] – [job reference] – Rev [A] Dear [name], please find attached our RAMS pack for [description of works] at [site], starting [date]. The pack index is on page 1. Please confirm acceptance, or send any comments, by [date], so we can deal with them before we start. Kind regards, [name, role]

| ✓ | RAMS pack index – tick what is included | Notes |
| --- | --- | --- |
| ☐ | Pack index and cover: job reference, site, client, revision and issue date |  |
| ☐ | Method Statement (ARB-SITE-005), approved | Rev: |
| ☐ | Generic risk assessments that apply (list) |  |
| ☐ | Pre-start SSRA (only if the client asked; completed on the day) |  |
| ☐ | COSHH assessments |  |
| ☐ | Insurance certificates (in date) | Expiry: |
| ☐ | Training matrix or certificates; plant inspection and LOLER records |  |
| ☐ | Permissions: TPO / CA, felling licence, highway permit, network operator agreement |  |
| ☐ | Wildlife check, rigging plan, traffic plan, tree protection plan, biosecurity plan (as needed) |  |
| ☐ | Accreditation certificates (e.g. CHAS, Constructionline, ARB Approved Contractor) |  |

5     Records and evidence

Section 5 of 5  ·  About 1 minute to read  ·  Office, Manager

| What to keep | Where | How long | Why |
| --- | --- | --- | --- |
| Final RAMS pack as issued, and every superseded revision | Job file → RAMS folder | [6 years] after the job | Shows what we told the client and what the crew followed. |
| Issue email or portal receipt, and client acceptance | Job file → RAMS folder | [6 years] after the job | Proves the pack was issued on time and accepted. |
| Signed SSRA and Method Statement briefing log | Job file | [6 years] after the job | Proves everyone on site was briefed (auditors ask). |
| RAMS log: job, revision, date issued, approved by, accepted | Office | Live, plus [6 years] | Quick evidence for audits and tenders (ARB-ACP-05). |

Guidance for the business owner – remove before issue How to use this procedure. Add your GRA library reference, the issue deadline and names in [red], and delete this box before issue. Keep this procedure in step with ARB-SITE-004 and ARB-SITE-005: if you change a form, check the section numbers here. The law (checked 27/09/2026). Management of Health and Safety at Work Regulations 1999, reg 3: a suitable and sufficient risk assessment, with significant findings recorded if you have 5 or more employees. Health and Safety at Work etc. Act 1974, s2: a safe system of work. Work at Height Regulations 2005, reg 4: work at height properly planned, including rescue. LOLER 1998, reg 8: lifting operations (rigging) planned by a competent person. CDM 2015 applies where the work is construction work, e.g. site clearance for a building project: see Method Statement section 1. HSE says method statements set out how a job will be done safely with all the control measures, and are recommended for higher-risk work ("Administration", HSE construction pages). "RAMS" is not a legal term; clients and principal contractors ask for it by contract. Our rules, not the law. The 48-hour issue time comes from the original procedure and common contract terms. "No aerial rescuer, no climb", the 10 m and 2 tree lengths power line rules and the on-the-day SSRA are company rules in ARB-POL-01 based on HSE and industry guidance. Changes from the original. All steps, controls and triggers are kept. Step 3 of the original ("create the SSRA in the office") now matches ARB-POL-01 and ARB-SITE-004: the office writes the site-specific hazards into the Method Statement and, if asked, a pre-start SSRA; the Team Leader completes the SSRA on the day. The GRA library is now your own library [ref]. Arborella provides this template as documentation support. It is not technical arboricultural or health and safety advice, and it does not replace your competent person’s judgement on the method.

## Related documents

| Reference | Document |
| --- | --- |
| ARB-SITE-005 | Method Statement (RAMS) |
| ARB-SITE-004 | Site Specific Risk Assessment and Crew Briefing |
| ARB-SITE-001 | Tree Survey and Quotation Form |
| ARB-POL-01 | Health and Safety Policy (5.1, 7, 10.2, 11.1) |
| ARB-ACP-08 | Quote to Invoice |
| [ref] | Generic Risk Assessments and COSHH assessments |

## Document control

| Document | RAMS Preparation Pack (ARB-ACP-07) |
| --- | --- |
| Owner | Company Director |
| Approved by | [Name, role] |
| Status | Controlled template – Live once approved |
| Review | At least every 12 months, and sooner if the law, guidance or the way we work changes |

| Ver. | Date | Author | Summary of changes |
| --- | --- | --- | --- |
| 1.0 | [DATE] | [Initials] | First Edition Created |