[COMPANY NAME]  –  COMPANY PROCEDURE

QUOTE TO INVOICE

The controlled route every job follows, from the first enquiry to the paid invoice, so no permission, safety step, customer right or invoice is missed.

| Reference | Version | Date issued | Review date |
| --- | --- | --- | --- |
| ARB-ACP-08 | 2.0 | [DD/MM/YYYY] | [DD/MM/YYYY] |

| At a glance |  |
| --- | --- |
| What it is for | One traceable path for every domestic, commercial, local authority and utility job. |
| Who does it | Office Administrator (enquiries, permissions, invoicing), Surveyor or estimator (survey and quote), Office or Compliance Lead (RAMS), Team Leader (delivery). A Manager or Director oversees it. |
| When (the trigger) | Every enquiry, from the moment it arrives. |
| Time needed | The office steps take about 1–2 hours across a typical job. Permissions can add 6 to 8 weeks. |
| You will need | The job management system, ARB-SITE-001 Survey and Quote, ARB-SITE-002 Job Sheet, the cancellation form (ARB-POL-15 Appendix B), ARB-ACP-01, 02, 06 and 07. |
| What "done" looks like | Work done as quoted (plus agreed changes), signed off, invoiced and paid, with every stage recorded in the job system. |
| Where records go | The job file in the job management system. Kept for [6 years] after the job. |

Where this fits in the office flow

| Enquiry THIS FLOW | › | TPO / CA check ACP-01 THIS FLOW | › | Quote ACP-08 THIS FLOW | › | RAMS ACP-07 THIS FLOW | › | Job THIS FLOW | › | Invoice ACP-08 THIS FLOW | › | Credit control ACP-06 THIS FLOW |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

This procedure is the whole office flow. It calls up ARB-ACP-01 (TPO check), ARB-ACP-02 (application), ARB-ACP-07 (RAMS) and ARB-ACP-06 (credit control) at the right points.

The rule Every stage is done in order, unless a Manager authorises otherwise, and every stage is recorded in the job system. No quote without a TPO and conservation area check. No booking without written acceptance, permissions and RAMS where needed. No invoice that does not match the quote and agreed changes.

1     The gates

Section 1 of 5  ·  About 1 minute to read  ·  Everyone in the office

A job cannot pass a gate until the check is done and recorded.

| Before we… | This must be done and recorded | Where |
| --- | --- | --- |
| Send a quote | Survey done; TPO and conservation area status recorded (ARB-ACP-01) | ARB-SITE-001 Part A; job file |
| Book the job | Written acceptance; home customer cancellation rights dealt with; permissions in place; RAMS approved and issued where needed | ARB-SITE-001 Part B; ARB-ACP-02; ARB-ACP-07 |
| Start work | Job Sheet issued; SSRA done and crew briefed on the day; consent or notice in the job pack | ARB-SITE-002; ARB-SITE-004 |
| Invoice | Completion confirmed; changes recorded and agreed with the customer | ARB-SITE-002 sections 5 and 7 |

2     Step by step

Section 2 of 5  ·  Across the life of the job  ·  Office, Surveyor, Team Leader, Manager

| # | What to do | Who | Record it |
| --- | --- | --- | --- |
| 1 | Log the enquiry Enter every enquiry in the job management system the same day: customer name, address and postcode, phone and email, what they want done, how they found us, and any deadline. Reply within [1 working day] (ARB-POL-15). | Office | Job system: new enquiry and job reference |

| 2 | Survey the site (ARB-SITE-001 Part A) The Surveyor assesses the scope, access, public interface, utilities and overhead lines, wildlife, biosecurity and environmental constraints, and takes photos. Office follow-ups are ticked at the end of Part A. | Surveyor / estimator | ARB-SITE-001 Part A; photos in the job file |
| --- | --- | --- | --- |

| 3 | Check TPO and conservation area status (ARB-ACP-01) Complete ARB-ACP-01 before the quote is sent. Save the evidence in the job file and tag the job. | Office / Surveyor | Dated screenshot or council email; job tag |
| --- | --- | --- | --- |

| 4 | Send the quote (ARB-SITE-001 Part B) Send within [1 working day] of the visit, or tell the customer the new date. It must show: the scope tree by tree, exclusions, the total price including VAT and every compulsory charge, optional extras separately, validity, payment terms, deposit, our terms and conditions, and the complaints route. Home customers agreeing at home, on site, or by phone, email or online: give the cancellation information and the cancellation form (ARB-POL-15 Appendix B), on paper or by email if they agree, before they accept. Include the Privacy Notice (ARB-POL-05). If a TPO or conservation area applies, quote "subject to council consent" or "subject to the 6-week notice". | Surveyor / estimator; office sends | Quote in the job system; "Given to customer" ticks on Part B |
| --- | --- | --- | --- |

| 5 | Record the acceptance Get written acceptance: the signed Part B, an email, or online approval. Record the date. Home customers can cancel within 14 days. Only book work inside the 14 days if they ask us to, in writing (the signed tick on Part B, or an email or text). If they cancel, refund any payment, including the deposit, within 14 days. | Office | Acceptance date; express request (if any) saved |
| --- | --- | --- | --- |

| 6 | Get the permissions (ARB-ACP-02) Apply for TPO consent or give the conservation area notice, and arrange any felling licence, highway permit, network operator agreement or wildlife check ticked on the survey. TPO: do not book until consent is granted in writing – no reply from the council is not consent. Conservation area: book no earlier than the end of the 6-week notice, unless the council confirms sooner that it has no objection. | Office | Consent, notice and permits in the job file |
| --- | --- | --- | --- |

| 7 | Prepare RAMS where needed (ARB-ACP-07) Where the contract requires RAMS, or the work is higher risk, follow ARB-ACP-07. Never reuse a RAMS pack without a project-specific review. | Office / Compliance Lead; Manager approves | Approved RAMS pack and issue record |
| --- | --- | --- | --- |

| 8 | Schedule and deliver the job Book the job only when every "Book the job" gate is passed. Issue the Job Sheet (ARB-SITE-002) with sections 1 to 4 copied from the accepted quote. On the day, the Team Leader completes the SSRA and briefs the crew. Any change to the work or price is agreed with the customer before it is done, recorded in Job Sheet section 5 and confirmed in writing. The Team Leader gets the completion sign-off (section 7) or takes after photos if the customer is out. | Office books; Team Leader delivers | Job Sheet, signed SSRA, photos back in the job file |
| --- | --- | --- | --- |

| 9 | Invoice and monitor payment (ARB-ACP-06) Invoice within [2 working days] of completion, or on the agreed staged dates. The invoice must match the quote plus the agreed changes. Then follow ARB-ACP-06 for reminders and escalation. | Office | Invoice in the accounts system; Invoice Register |
| --- | --- | --- | --- |

3     When to stop, and an example

Section 3 of 5  ·  About 2 minutes to read  ·  Office, Manager

Stop – do not continue if… - the TPO or conservation area status is not recorded, or the council has not replied; - a home customer wants us to start within 14 days but has not asked in writing, or has not been given the cancellation information; - the customer asks for a "cash price" or no invoice (ARB-POL-07); - the Job Sheet does not match the accepted quote, or the crew is asked to do extra work that has not been agreed and priced; - RAMS are needed and not approved, or client comments are unresolved; - the invoice would differ from the quote without a recorded, agreed change. If any of these apply, stop and speak to [Manager name].

What this means for you A homeowner rings on Monday about an overgrown sycamore. You log it and the estimator visits on Tuesday. The council map shows a conservation area, so the quote goes out on Wednesday "subject to the 6-week notice", with the cancellation form and our Privacy Notice attached. She accepts by email on Thursday. The office gives the notice (ARB-ACP-02) the same day and books the job for the week after the notice ends. On the day she asks the crew to lift the crown of a holly too. The Team Leader prices it, records it in Job Sheet section 5 and gets her initials. The office invoices the sycamore plus the agreed holly work two days later.

Urgent work If a customer asks us to come out for urgent work, for example a split limb hanging over the road after a storm, there is no right to cancel for that urgent work. Anything extra agreed on the same visit does carry the right to cancel. Protected trees still need a Manager’s decision on the dead or dangerous exception (ARB-POL-29) and notice to the council. See ARB-POL-15 Section 3 and ARB-POL-17.

4     Templates

Section 4 of 5  ·  Copy, paste and fill in  ·  Office

Confirming a home customer’s acceptance Hello [name], thank you for accepting quote [Q-REF] for [work] at £[total inc VAT]. As you agreed this [at home / by email], you have 14 days to cancel if you change your mind; the cancellation form is attached. We will not start before [date] unless you ask us to. If you would like us to start sooner, please reply "Please start before the 14 days end". If you then cancel, you would pay only for work already done. Kind regards, [name]

Confirming a change agreed on site "Hello [name], thanks for today. As agreed with [Team Leader], we also [extra work] for £[price inc VAT], which will be added to your invoice. Please reply if anything is not as you expected."

5     Records and evidence

Section 5 of 5  ·  About 1 minute to read  ·  Office, Manager

| What to keep | Where | How long | Why |
| --- | --- | --- | --- |
| Enquiry record, survey (ARB-SITE-001 Part A) and photos | Job system / job file | [6 years] after the job | Shows what we saw and planned before pricing. |
| TPO / CA evidence, consents, notices and permits | Job file → Planning / TPO | [6 years] after the job | Proves permissions were in place before work. |
| Quote, acceptance, cancellation information given, express request to start | Job file | [6 years] after the job | Contract evidence; consumer law compliance. |
| RAMS pack, Job Sheet, signed SSRA, changes and completion sign-off | Job file | [6 years] after the job | Safety and delivery record; basis of the invoice. |
| Invoice, payments and chase notes | Accounts system | [6 years] from the end of the financial year | Accounting records law (ARB-ACP-06). |

Guidance for the business owner – remove before issue How to use this procedure. Set your response and invoicing times, fill in everything in [red], and delete this box before issue. Check your job management system records every stage (ARB-ACP-09). Consumer law (checked 27/09/2026, matches ARB-POL-15 and ARB-SITE-001). Consumer Contracts (Information, Cancellation and Additional Charges) Regulations 2013: off-premises and distance service contracts carry a 14-day cancellation right; off-premises information must be on paper, or another durable medium if the customer agrees (reg 10); work may start within 14 days only on the customer’s express request, on a durable medium for off-premises contracts (reg 36); a customer who cancels then pays a proportionate amount; refunds within 14 days of being told; not giving cancellation information for an off-premises contract is a criminal offence (reg 19), and it extends the cancellation period by up to 12 months. Urgent repairs the customer asked for are excluded, but extra services on that visit are not (reg 28). Since 6 April 2025 the headline price must include every compulsory charge (Digital Markets, Competition and Consumers Act 2024). Trees. TPO: the council should normally decide within 8 weeks; if it does not, the applicant can appeal, but the work still needs consent. Conservation areas: 6 weeks’ notice (s211 Town and Country Planning Act 1990). Dead trees: 5 working days’ notice. See ARB-ACP-01, ARB-ACP-02 and ARB-POL-29. VAT. VAT-registered businesses issue a VAT invoice to VAT-registered customers within 30 days of the time of supply (HMRC VATREC6010). Tree work that is part of construction may fall under CIS and the VAT domestic reverse charge: ask your accountant. Errors fixed from the original. It allowed booking once "the statutory period expires" for any planning check. That is right for conservation area notices but not for TPOs: silence from the council is not consent. It also had no customer cancellation rights, price rules or change control. Owner decision: the original applied for permissions before acceptance. This version applies after acceptance, so you do not make free applications; change step 6 if you prefer to apply first. Arborella provides this template as documentation support. It is not legal advice, and it does not replace advice on your terms and conditions.

## Related documents

| Reference | Document |
| --- | --- |
| ARB-SITE-001 | Tree Survey and Quotation Form |
| ARB-SITE-002 | Job Sheet |
| ARB-POL-15 | Customer Care and Complaints Policy (cancellation form, Appendix B) |
| ARB-ACP-01 / 02 | TPO and Conservation Area Status Check / Application |
| ARB-ACP-06 / 07 | Invoice Chasing and Credit Control / RAMS Preparation Pack |
| ARB-ACP-09 | Job Management Software Workflow |

## Document control

| Document | Quote to Invoice (ARB-ACP-08) |
| --- | --- |
| Owner | Company Director |
| Approved by | [Name, role] |
| Status | Controlled template – Live once approved |
| Review | At least every 12 months, and sooner if the law, guidance or the way we work changes |

| Ver. | Date | Author | Summary of changes |
| --- | --- | --- | --- |
| 1.0 | [DATE] | [INITIALS] | First Edition Created |